## Group C (471 Winter 2020)
Activity | Task | Subtask | Subtask description | Status | Estimation | Release | Personas
Children "calling" 911 in demonstrations / at home | Kids login to phone
Children "calling" 911 in demonstrations / at home | Kids navigate to, and open an app | Create interface similar to phone app for kids to navigate through |  | Todo |  | Release 1
Children "calling" 911 in demonstrations / at home | Kids navigate to, and open an app | Point system is added to app to gamify it. |  | Todo |  | Release 3 (Down the line)
Children "calling" 911 in demonstrations / at home | Practice remembering information for call. | Give prompts in app for kids to answer |  | Todo |  | Release 1
Children "calling" 911 in demonstrations / at home | Kids call 911, and talk to firefighter/parent | Create flow that simulates kid dialing and calling 911 |  | Todo |  | Release 2
Children "calling" 911 in demonstrations / at home | Kids call 911, and talk to firefighter/parent | Kid talks to simulated voice that prompts them |  | Todo |  | Release 3 (Down the line)
Children "calling" 911 in demonstrations / at home | Kids call 911, and talk to firefighter/parent | App has built-in voice recognition that listens for key words/phrases |  | Todo |  | Release 3 (Down the line)
Setting up a simulated 911 call in demonstrations / at home | Firefighter sets up two phones | Make 911 simulation app downloadable |  | Todo |  | Release 2
Setting up a simulated 911 call in demonstrations / at home | Firefighter/parent and child talk to each other, pretending to phone
Giving parents info about fire safety | Parents follow a link in an email to download an app | Create accessible link for parents |  | Todo |  | Release 1
Giving parents info about fire safety | Parents follow a link in an email to download an app | Link to app is accessible and app is downloadable through email |  | Todo |  | Release 2
Giving parents info about fire safety | Read easily digestible information in the app | Display fire safety info in app |  | Todo |  | Release 1
Giving parents info about fire safety | App prompts parents to simulate a call with their child. | Develop prompt interface that guides parents through questions |  | Todo |  | Release 1
Note on A2: Kids don't know what to say to 911 operators when they are trying to report a fire. Kids would use the app to login, navigate to a phone app, dial, call and communicate with a pretend 911 operator. A kid in a fire situation would remember what they had learned and help get help as soon as possible.
Note on B2: As a kid, I want to be able to login to a familiar looking phone, so that I can call 911.
Note on B3: As a kid, I want to be able to find and use a familar phone app, so that I would be able to do the same on a real phone.
Note on B5: As a child, I want to be able to practice saying the things I learned at the school demonstration, so that I would be ready to repeat them to a real worker.
Note on B6: As a kid, I want to dial and call 911 because I want to practice what to say.
Note on A9: Firefighters want to teach kids how to phone 911, but kids don't know how to use landlines anymore, and the firefighters don't have a modern way of simulating a 911 call. Firefighters would want to use an app that allows them to set up an interface that looks and acts just like a regular phone app that would instead direct the kids to answer firefighter's questions when prompted. Firefighters and parents would use this app to practice simulating calls to 911 with the kids.
Note on B9: As a firefighter, I want to be able to set up two phones, one for me, and one for the child, so that a child may talk to me as if they called 911 in the demonstration.
Note on B10: As a firefighter/parent, I want to pretend to talk to the child through the phone in order to ask them to give information about their fire situation.
Note on B11: As a parent, I want to be able to see the information my child is learning so that I can help us protect ourselves in the event of a fire.
Note on B13: As a parent, I want to quickly and easily read information from my child, because my time is very important.
Note on B14: As a parent, I want to allow my child to answer questions, because they are excited to know the answers.

## Releases
Name | Goal | Start date | Release date | Is released | Is archived
Release 1 |  |  |  | False | False
Release 2 |  |  |  | False | False
Release 3 (Down the line) |  |  |  | False | False